## Worksheet
Data Outstanding Work Order
No | No Work Order | Nama Work Order | Department | Tanggal | Target | Status | Progress | PIC
1 | HM-0007 | penggantian lampu di GD7 Update donk | Logistik | 06 Apr 21 | 08 Apr 21 | Open | Approval | Hasanudin
2 | HM-127-XII-21 | SS Buat Identitas Nozel | Production | 16 Dec 21 | 17 Dec 21 | Open | Created | Susanto
3 | HM-126-IX-21 | Buat colokan Printer | Production | 03 Sep 21 | 10 Sep 21 | Open | Approval | Elman Firmansyah
4 | HM-125-VIII-21 | Tempat Nozel Pad Pillar | Production | 27 Aug 21 | 03 Sep 21 | Open | Approval | Susanto
5 | HM-124-VI-21 | Display Control Pembelian FPP | Human Resource | 03 Jun 21 | 17 Jun 21 | Open | Approval | Arandika
6 | HM-123-V-21 | Perbaikan atap dapur Office mall | Human Resource | 07 May 21 | 22 May 21 | Open | Approval | Dendy Ranjeng
7 | HM-120-V-21 | Alat bantu angkat RP | Production | 06 May 21 | 29 May 21 | Open | Approval | Susanto
8 | HM-121-V-21 | Pasang kabel LAN | Information Technologi | 06 May 21 | 14 May 21 | Open | Created | Reza
9 | HM-122-V-21 | coba coba | Production | 06 May 21 | 19 May 21 | Open | Approval | Elman Firmansyah
10 | HM-114-V-21 | Meja tempat berkas | Human Resource | 05 May 21 | 21 May 21 | Open | Approval | Arandika
11 | HM-115-V-21 | Meja kerja | Human Resource | 05 May 21 | 29 May 21 | Open | Approval | Arandika
12 | HM-116-V-21 | Display kehadiran karyawan | Human Resource | 05 May 21 | 22 May 21 | Open | Approval | Maria Goreti
13 | HM-117-V-21 | Display limit sample butyl tape | Human Resource | 05 May 21 | 29 May 21 | Open | Approval | Maria Goreti
14 | HM-118-V-21 | Rak arsip GA | Human Resource | 05 May 21 | 29 May 21 | Open | Approval | Dendy Ranjeng
15 | HM-119-V-21 | Display Control FIFO Pembelian | Human Resource | 05 May 21 | 22 May 21 | Open | Approval | Susanto
16 | HM-113-IV-21 | Mal untuk proses packing | Production | 22 Apr 21 | 24 Apr 21 | Open | Approval | Watno
17 | HM-112-IV-21 | Display limit sample butyl tape | Production | 21 Apr 21 | 17 Apr 21 | Open | Approval | Susanto
18 | HM-111-IV-21 | Display Control FIFO | Production | 21 Apr 21 | 30 Apr 21 | Open | Approval | Susanto
19 | HM-110-IV-21 | Mal untuk proses packing | Production | 20 Apr 21 | 21 Apr 21 | Open | Approval | Susanto
20 | HM-109-IV-21 | Alat menghitung Stiffener | Production | 16 Apr 21 | 23 Apr 21 | Open | Approval | Elman Firmansyah
21 | HM-108-IV-21 | Pasang TV Mobility di Line STF | Production | 09 Apr 21 | 14 Apr 21 | Open | Approval | Susanto
22 | HM-107-IV-21 | Alat menghitung Pad Pillar | Production | 08 Apr 21 | 16 Apr 21 | Open | Approval | Susanto
23 | HM-0008 | Pemasangan Saklar On-OFF untuk display timbangan d | Production | 07 Apr 21 | 07 Apr 21 | Open | Approval | Ardha Dyota Ahimsa
24 | HM-0004 | pergantian lampu LED di gudang 3 | Logistik | 06 Apr 21 | 08 Apr 21 | Open | Cash out | Hasanudin
25 | HM-0005 | Pembuatan Chuter Line DFAS2 (New Dfoam) | Operation System | 06 Apr 21 | 16 Apr 21 | Open | Waiting list | Siti Yusriani
26 | HM-0006 | Pembuatan Rak D-fom D55 | Logistik | 06 Apr 21 | 09 Apr 21 | Open | Cash out | Hasanudin
27 | HM-0003 | Pergantian Lampu di Parkiran depan | Human Resource | 05 Apr 21 | 06 Apr 21 | Open | Approval | Dendy Ranjeng
28 | HM-0001 | Pembuatan Rak D-fom D55 | Logistik | 05 Apr 21 | 09 Apr 21 | Open | Waiting list | Hasanudin
29 | HM-105-III-21 | Tambhan lampu neon | Production | 26 Mar 21 | 02 Apr 21 | Open | Waiting list | Sarip Hidayat
30 | HM-104-III-21 | Pembuatan stoper dan pengecatan | Production | 26 Mar 21 | 02 Apr 21 | Open | Waiting list | Sarip Hidayat
31 | HM-102-III-21 | Pembuatan kanopi di gudan g7 dekat stiffener ajkd | Production | 25 Mar 21 | 01 Apr 21 | Open | In progress | Watno
32 | HM-097-III-21 | Menghilangkan hasil cutting pendek | Production | 23 Mar 21 | 30 Mar 21 | Open | Purchasing | Watno
33 | HM-095-III-21 | Dudukan roll plastik | Production | 19 Mar 21 | 26 Mar 21 | Open | Waiting list | Watno
34 | HM-094-III-21 | Safety tutup cup mesin | Production | 19 Mar 21 | 26 Mar 21 | Open | Waiting list | Watno
35 | HM-092-III-21 | Menutup lubang saluran air | Human Resource | 17 Mar 21 | 24 Mar 21 | Open | Waiting list | Maria Goreti
36 | HM-087-III-21 | Pembuatan mesin press com | Technical | 16 Mar 21 | 23 Mar 21 | Open | In progress | Anastasia Ratri Astuti
37 | HM-086-III-21 | Perbaikan KOB | Logistik | 12 Mar 21 | 19 Mar 21 | Open | Waiting list | Sugiarto
38 | HM-077-III-21 | Pemasangan indikator RPM | Production | 08 Mar 21 | 15 Mar 21 | Open | Handover | Susanto
39 | HM-039-II-21 | Menaruh produk stiffener | Production | 08 Feb 21 | 15 Feb 21 | Open | Handover | Watno